## User Stories
USER STORIES
Issue Type | Summary
Epic | Payment page
Story1 | As a user , I want to do Payment with UPI option.
Task1 | As a user ,I want to view UPI drop down button.
Task2 | As a user ,I want tor click on UPI drop down user should able to view the "Enter UPI ID" .
Task3 | As a user ,I want to click on Enter UPI ID user should navigate to "ENTER UPI ID" page.
Task4 | As a user ,I want to enter valid UPI ID
Task5 | Then they will be verify button.
Task6 | After entering the valid UPI ID user should click on the verify button.
Story2 | As a user , I want to do Payment with Wallet option.
Task1 | As a user ,I want to view Wallet drop down button
Task2 | As a user ,I want to click on Wallet drop down user should able to view Paytm, Phonepe and Mobikwik.
Task3 | As a user ,I want to select the Paytm Option to do money transactions.
Task4 | As a user ,I want to select the Phonepe Option to do money transactions
Task5 | As a user ,I want to select the Mobikwik Option to do money transactions.
Story3 | As a user , I want to do Payment with Debit/Credit Card option.
Task1 | As a user ,I want to view Debit/Credit Card drop down button.
Task2 | As a user ,I want to click on Debit/Credit Card drop down Button user should able to view the Add new card.
Task3 | As a user ,I want to click on Add new card user should navigate to "Add NEW DEBIT/CREDIT CARD" page.
Task4 | As a user ,I want to enter valid Card Number in Card Number text field.
Task5 | As a user ,I want to enter valid Expiry Date in Expiry Date text field.
Task6 | As a user ,I want to enter valid CVV in CVV text field.
Task7 | Then they will be verify button.
Task8 | After entering the valid DEBIT/CREDIT details user should click on the verify button.
Story4 | As a user , I want to do Payment with Net Banking option.
Task1 | As a user ,I want to view Net Banking drop down button.
Task2 | As a user ,I want to click on Net Banking drop down user should able to view the View all banks.
Task3 | As a user ,I want to click on View all banks user should navigate to "SEARCH ALL BANKS" page.
Task4 | As a user ,I want to enter valid bank name in Search your bank name text field.
Task5 | As a user ,I want to select the bank in the result bank name list.
Task6 | Then they will be Select button.
Task7 | After entering the valid bank name user should click on the Select button.
Story5 | As a user , I want to do Payment with Cash on Delivery option.
Task1 | As a user ,I want to view Cash on Delivery drop down button.
Task2 | As a user ,I want to click on Cash on Delivery drop down button.
Task3 | Then Pay cash on delivery is automatically selected.
Story6 | As a user ,I want to view Reselling the order.
Task1 | By default "No" option is selected in Reselling the order.
Task2 | As a user ,I want to click on "Yes" user should able to view the "Order Total + Your Margin".
Task3 | As a user ,I want to click on Order Total + Your Margin in "Order Total + Your Margin" text field page.
Task4 | As a user ,I want to enter amount of user Margin.
Task5 | Then they will be Continue button.
Task6 | After entering the amount user should click on the Continue button.

## Test Scenarios
TEST SCENARIO TEMPLATE
Test Scenario ID | Requirement ID | Test Scenario Description | Type of Testing | Possible No of Test Cases | Test Case Details
TS_UPI_01 | Req_UPI_01 | Verify user is able to Buy a item using UPI. | Integration | 3 | 1. Verify user is able to add the UPI ID by clicking on Enter UPI ID in UPI drop down button. 2. Verify user is able to Enter the characters in UPI ID in UPI ID text field. 3. Verify user able to verify the verify Button by click on it.
TS_Wallet_01 | Req_Wallet_01 | Verify user is able to Buy a item using Wallet. | Integration | 4 | 1. Verify user able to select Wallet drop down button. 2. Verify user is able to Buy product using Paytm Radio Button. 3. Verify user is able to Buy product using Phonepe Radio Button. 4. Verify user is able to Buy product using Mobikwik Radio Button.
TS_Debit/Credit Card_01 | Req_Debit/Credit Card_01 | Verify user is able to Buy a item using Debit/Credit Card. | Integration | 5 | 1. Verify user is able to add the Add new card by clicking on Add new card in Debit/Credit Card drop down button. 2. Verify user able to enter the Card Number in Enter Card Number Text filed. 3. Verify user able to enter the Expiry Date in Expiry Date Text filed. 4. Verify user able to enter the CVV in CVV Text filed. 5. Verify user able to verify the verify Button by click on it.
TS_Net Banking_01 | Req_Net Banking_01 | Verify user is able to Buy a item using Net Banking. | Integration | 4 | 1. Verify user is able to add the Bank name by clicking on View all bank in Nat Banking drop down button. 2. Verify user able to enter the Bank name in Search your bank name Text filed. 3. Verify user able to Select the Bank by clicking on it. 4. Verify user able to Select the Select Button by click on it.
TS_Cash on Delivery_01 | Req_Cash on Delivery_01 | Verify user is able to Buy a item using Cash on Delivery. | Functionality | 1 | 1. Verify user is able to Select the Pay Cash on delivery by clicking on Cash on Delivery drop down button.
TS_Reselling the Order_01 | Req_Reselling the Order_01 | Verify user is able to Buy a item using Reselling the order. | Functionality | 3 | 1. Verify user able to view "No" and "Yes" radio Buttons in Reselling the oredr. 2. Verify user able to Select the "No" and "Yes" radio Buttons in Reselling the oredr. 3. Verify user able to enter the Amount in your margin Text filed.
TS_Buy Now_01 | Req_Buy Now_01 | Verify user is able to Buy product. | System | 3 | 1. Verify user is able to Buy product. 2. Verify user is able to Buy a Shirt by Selecting Size. 3. Verify user is able to Buy a item by Add to Cart.

## Test Case Template
TEST CASE TEMPLATE
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result | Status
TC_UPI_01 | TS_UPI_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a item using UPI. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on UPI . 9. Click on Contunue. 10. Click on Pay Now. 11. Click on Place Order. | 1. Search : item 2. Payment : UPI. | user is able to Buy a item using UPI. | user is able to Buy a item using UPI. | Pass.
TC_UPI_02 | TS_UPI_01 | open the browser enter the url signup with user credentials | Verify user is able to add the UPI ID by clicking on Enter UPI ID in UPI drop down button. | 1. open the Meesho app. 2. Search for the Product. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select UPI Option. 9. Click on Enter UPI ID. 10. Enter the UPI ID in UPI ID text Field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Place Order. 14. Click on Pay Now. | 1. Search : item 2. Payment : UPI. 3. UPI ID : abcd@paytm | user is able to add the UPI ID by clicking on Enter UPI ID in UPI drop down button | user is able to add the UPI ID by clicking on Enter UPI ID in UPI drop down button | Pass.
TC_UPI_03 | TS_UPI_01 | open the browser enter the url signup with user credentials | Verify user is able to Enter the characters in UPI ID in UPI ID text field. | 1. open the Meesho app. 2. Search for the Product. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select UPI Option. 9. Click on Enter UPI ID. 10. Enter the UPI ID in UPI ID text Field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Place Order. 14. Click on Pay Now. | 1. Search : item 2. Payment : UPI. 3. UPI ID : abcd@paytm | user is able to Enter the characters in UPI ID in UPI ID text field. | user is able to Enter the characters in UPI ID in UPI ID text field. | Pass.
TC_UPI_04 | TS_UPI_01 | open the browser enter the url signup with user credentials | Verify user able to verify the verify Button by click on it. | 1. open the Meesho app. 2. Search for the Product. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select UPI Option. 9. Click on Enter UPI ID. 10. Enter the UPI ID in UPI ID text Field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Place Order. 14. Click on Pay Now. | 1. Search : item 2. Payment : UPI. 3. UPI ID : abcd@paytm | user able to verify the verify Button by click on it. | user able to verify the verify Button by click on it. | Pass.
TC_UPI_05 | TS_UPI_01 | open the browser enter the url signup with user credentials | Verify user is not able to Buy a item by using invalied UPI ID datiles. | 1. open the Meesho app. 2. Search for the Product. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select UPI Option. 9. Click on Enter UPI ID. 10. Enter the UPI ID in UPI ID text Field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Place Order. 14. Click on Pay Now. | 1. Search : item 2. Payment : UPI ID. 3. UPI ID : jshsksbi | user is not able to Buy a item by using invalied UPI ID datiles. | user is not able to Buy a item by using invalied UPI ID datiles. | Pass.
TC_Wallet_01 | TS_Wallet_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a item using Wallet. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on Wallet. 9. Click on Contunue. 10. Click on Pay Now. 11. Click on Place Order. | 1. Search : item 2. Payment : Wallet. | user is able to Buy a item using Wallet. | user is able to Buy a item using Wallet. | Pass.
TC_Wallet_02 | TS_Wallet_01 | open the browser enter the url signup with user credentials | Verify user able to select Wallet drop down button. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on Wallet. | 1. Search : item | user able to select Wallet drop down button. | user able to select Wallet drop down button. | Pass.
TC_Wallet_03 | TS_Wallet_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy product using Paytm Radio Button. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on Wallet. 9. Select the Paytm Radio button. 9. Click on Contunue. 10. Click on Pay Now. 11. Click on Place Order. | 1. Search : item 2. Payment : Wallet. | user is able to Buy product using Paytm Radio Button. | user is able to Buy product using Paytm Radio Button. | Pass.
TC_Wallet_04 | TS_Wallet_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy product using Phonepe Radio Button. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on Wallet. 9. Select the Phonepe Radio button. 9. Click on Contunue. 10. Click on Pay Now. 12. Click on Place Order. | 1. Search : item 2. Payment : Wallet. | user is able to Buy product using Phonepe Radio Button. | user is able to Buy product using Phonepe Radio Button. | Pass.
TC_Wallet_05 | TS_Wallet_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy product using Mobikwik Radio Button. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on Wallet. 9. Select the Mobikwik Radio button. 9. Click on Contunue. 10. Click on Pay Now. 13. Click on Place Order. | 1. Search : item 2. Payment : Wallet. | user is able to Buy product using Mobikwik Radio Button. | user is able to Buy product using Mobikwik Radio Button. | Pass.
TC_Wallet_06 | TS_Wallet_01 | open the browser enter the url signup with user credentials | Verify user is not able to Buy product using Amazon Pay. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on Wallet. 9. Select the Amazon Pay. | 1. Search : item 3. Payment : Wallet. | user is not able to Buy product using Amazon Pay | user is not able to Buy product using Amazon Pay | Faile
TC_Debit/Credit Card_01 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a item using Debit/Credit Card. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter Card Number,Expiry Date and CVV. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Pay Now. 14. Click on Place Order. | 1. Search : item 2. Payment : Credit Card. 3. Card NO:2345 5467 8984 8645. 4. Expiry Date: 04/28. 5. CVV : 435. | user is able to Buy a item using Debit/Credit Card. | user is able to Buy a item using Debit/Credit Card. | Pass.
TC_Debit/Credit Card_02 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user is able to add the Add new card by clicking on Add new card in Debit/Credit Card drop down button. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter Card Number,Expiry Date and CVV. 11.Click on verify Button. | 1. Search : product 2. Payment : Debit Card. 3. Card NO:2345 5467 8984 8645. 4. Expiry Date: 04/28. 5. CVV : 435. | user is able to add the Add new card by clicking on Add new card in Debit/Credit Card drop down button. | user is able to add the Add new card by clicking on Add new card in Debit/Credit Card drop down button. | Pass.
TC_Debit/Credit Card_03 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | erify user able to enter the Card Number in Enter Card Number Text filed. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter Card Number. 11.Click on verify Button. | 1. Search : product 2. Payment : Debit Card. 3. Card NO:2345 5467 8984 8645. | user able to enter the Card Number in Enter Card Number Text filed | user able to enter the Card Number in Enter Card Number Text filed | Pass.
TC_Debit/Credit Card_04 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user able to enter the Expiry Date in Expiry Date Text filed. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter Expiry Date. | 1. Search : product 2. Payment : Debit Card. 3. Expiry Date: 04/28. | user able to enter the Expiry Date in Expiry Date Text filed. | user able to enter the Expiry Date in Expiry Date Text filed. | Pass.
TC_Debit/Credit Card_05 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user able to enter the CVV in CVV Text filed. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter CVV.. | 1. Search : product 2. Payment : Debit Card. 3. CVV : 435. | user able to enter the CVV in CVV Text filed. | user able to enter the CVV in CVV Text filed. | Pass.
TC_Debit/Credit Card_06 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user able to verify the verify Button by click on it. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter Card Number,Expiry Date and CVV. 11.Click on verify Button. | 1. Search : product 2. Payment : Debit Card. 3. Card NO:2345 5467 8984 8645. 4. Expiry Date: 04/28. 5. CVV : 435. | user able to verify the verify Button by click on it. | user able to verify the verify Button by click on it. | Pass.
TC_Debit/Credit Card_07 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user Should not able to enter more then 12 numbers in Card Number in Debit Card. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter more then 12 numbers in Card Number field. 11.Click on verify Button. | 1. Search : product 2. Payment : Debit Card. 3. Card NO:2345 5467 8984 8645 5647. | user Should not able to enter more then 12 numbers in Card Number in Debit Card. | user Should not able to enter more then 12 numbers in Card Number in Debit Card. | Pass.
TC_Debit/Credit Card_08 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user Should not able to enter more then 3 numbers in CVV in Debit Card. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter more then 3 numbers in CVV field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Pay Now. 14. Click on Place Order. | 1. Search : product 2. Payment : Debit Card. 3. CVV : 43545. | user Should not able to enter more then 3 numbers in CVV in Debit Card. | user Should not able to enter more then 3 numbers in CVV in Debit Card. | Pass.
TC_Debit/Credit Card_09 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user not able to buy a product by entering inavlied Debit Card details. | 1. open the Meesho app. 2. Search for the Product. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Click on verify Button. 11. Click on Contunue. 12. Click on Pay Now. 13. Click on Place Order. | 1. Search : product 2. Payment : Debit Card. 3. Card NO:2345 5467 8984 8645. 4. Expiry Date: 04/28. 5. CVV : 435. | user not able to buy a product by entering inavlied Debit Card details. | user not able to buy a product by entering inavlied Debit Card details. | Pass.
TC_Debit/Credit Card_10 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user Should not able to enter less then 12 numbers in Card Number in Debit Card. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter less then 12 numbers in Card Number field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Pay Now. 14. Click on Place Order. | 1. Search : product 2. Payment : Debit Card. 3. Card NO:2345 5467 898. | user Should not able to enter less then 12 numbers in Card Number in Debit Card. | user Should not able to enter less then 12 numbers in Card Number in Debit Card. | Pass.
TC_Debit/Credit Card_11 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user Should not able to enter less then 3 numbers in CVV in Debit Card. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter less then 3 numbers in Card Number field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Pay Now. 14. Click on Place Order. | 1. Search : product 2. Payment : Debit Card. 3. CVV : 43. | user Should not able to enter less then 3 numbers in CVV in Debit Card. | user Should not able to enter less then 3 numbers in CVV in Debit Card. | Pass.
TC_Debit/Credit Card_12 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user able to enter the valied Expiry Date in Expiry Date Text filed. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Enter Expiry Date. | 1. Search : product 2. Payment : Debit Card. 3. Expiry Date: 04/28. | user able to enter the valied Expiry Date in Expiry Date Text filed. | user able to enter the valied Expiry Date in Expiry Date Text filed. | Pass.
TC_Debit/Credit Card_13 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user Should notable to enter the invalied Expiry Date in Expiry Date Text filed. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 11.Enter Expiry Date. | 1. Search : product 2. Payment : Debit Card. 3. Expiry Date: 28/29. | user Should notable to enter the invalied Expiry Date in Expiry Date Text filed | user Should notable to enter the invalied Expiry Date in Expiry Date Text filed | Pass.
TC_Debit/Credit Card_14 | TS_Debit/Credit Card_01 | open the browser enter the url signup with user credentials | Verify user not able to buy a product by entering inavlied Debit Card details. | 1. open the Meesho app. 2. Search for the Product. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select Debit Card Option. 9. Click on Add new Card. 10.Click on verify Button. 11. Click on Contunue. 12. Click on Pay Now. 13. Click on Place Order. | 1. Search : product 2. Payment : Debit Card. 3. Card NO:2345 5467 8984 8645. 4. Expiry Date: 04/28. 5. CVV : 435. | user not able to buy a product by entering inavlied Debit Card details. | user not able to buy a product by entering inavlied Debit Card details. | Pass.
TC_Net Banking_01 | TS_Net Banking_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a item using Net Banking. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on Net Banking. 9. Click on Contunue. 10. Click on Pay Now. 11. Click on Place Order. | 1. Search : item 2. Payment : Net Banking. | user is able to Buy a item using Net Banking. | user is able to Buy a item using Net Banking. | Pass.
TC_Net Banking_02 | TS_Net Banking_01 | open the browser enter the url signup with user credentials | Verify user is able to add the Bank name by clicking on View all bank in Nat Banking drop down button. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on Net Banking. 8. Click on View all bank. 9. Enter the Bank Name in Search bar. 10. Select the Bank. 11. Click on Select Button. | 1. Search : item 2. Payment : Net Banking. 3. Search : canara bank. | user is able to add the Bank name by clicking on View all bank in Nat Banking drop down button. | user is able to add the Bank name by clicking on View all bank in Nat Banking drop down button. | Pass.
TC_Net Banking_03 | TS_Net Banking_01 | open the browser enter the url signup with user credentials | Verify user able to enter the Bank name in Search your bank name Text filed. | . open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on Net Banking. 8. Click on View all bank. 9. Enter the Bank Name in Search bar. 10. Select the Bank. 11. Click on Select Button. | 1. Search : item 2. Payment : Net Banking. 3. Search : SBI bank. | Verify user able to enter the Bank name in Search your bank name Text filed. | Verify user able to enter the Bank name in Search your bank name Text filed. | Pass.
TC_Net Banking_04 | TS_Net Banking_01 | open the browser enter the url signup with user credentials | Verify user able to Select the Bank by Searching bank name in Search all bank. | . open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on Net Banking. 8. Click on View all bank. 9. Enter the Bank Name in Search bar. 10. Select the Bank. 12. Click on Select Button. | 1. Search : item 2. Payment : Net Banking. 4. Search : SBH bank. | user able to Select the Bank by clicking on it. | user able to Select the Bank by clicking on it. | Pass.
TC_Net Banking_05 | TS_Net Banking_01 | open the browser enter the url signup with user credentials | Verify user able to Select the Select Button by click on it. | . open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on Net Banking. 8. Click on View all bank. 9. Enter the Bank Name in Search bar. 10. Select the Bank. 13. Click on Select Button. | 1. Search : item 2. Payment : Net Banking. 5. Search : SBI bank. | ser able to Select the Select Button by click on it. | user able to Select the Select Button by click on it. | Pass.
TC_Net Banking_06 | TS_Net Banking_01 | open the browser enter the url signup with user credentials | Verify user is not able to Search using invalied bank name | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on Net Banking. 8. Click on View all bank. 9. Enter the Bank Name in Search bar. 10. Select the Bank. 11. Click on Select Button. | 1. Search : item 2. Payment : Net Banking. 3. Search : SSBBII bank. | user is not able to Search using invalied bank name | user is not able to Search using invalied bank name | Pass.
TC_Net Banking_07 | TS_Net Banking_01 | open the browser enter the url signup with user credentials | Verify user is able to Navigate View all bank page in Net Banking Option. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on Net Banking. 8. Click on View all bank. 9. Enter the Bank Name in Search bar. 10. Select the Bank. 11. Click on Select Button. 12. Click on Contunue. 13. Click on Pay Now Button. 14. Click on Place Order. | 1. Search : item 2. Payment : Net Banking. 3. Search : canara bank. | user is able to Navigate View all bank page in Net Banking Option. | user is able to Navigate View all bank page in Net Banking Option. | Pass.
TC_Cash on Delivery_01 | TS_Cash on Delivery_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a item using Cash on Delivery. | 1. open the Meesho app. 2. Select the product. 3.Click on Buy Now button. 4. Select the address. 5. Click on Deliver To This Address. 6. Select the Payment method. 7. Click on COD. 8. Click on Contunue. 9. Click on Place Order. | 1. Search : Product 2. Payment : COD. | user is able to Buy a item using Cash on Delivery. | user is able to Buy a item using Cash on Delivery. | Pass.
TC_Cash on Delivery_02 | TS_Cash on Delivery_01 | open the browser enter the url signup with user credentials | Verify user is able to Select the Pay Cash on delivery by clicking on Cash on Delivery drop down button. | 1. open the Meesho app. 2. Select the product. 3.Click on Buy Now button. 4. Select the address. 5. Click on Deliver To This Address. 6. Select the Payment method. 7. Click on COD. 8. Click on Pay cash on delivery. 8. Click on Contunue. 10. Click on Place Order. | 1. Search : Product 3. Payment : COD. | user is able to Select the Pay Cash on delivery by clicking on Cash on Delivery drop down button. | user is able to Select the Pay Cash on delivery by clicking on Cash on Delivery drop down button. | Pass.
TC_Cash on Delivery_03 | TS_Cash on Delivery_01 | open the browser enter the url signup with user credentials | Verify user is not able to Buy a Shirt with out Selecting Size. | 1. open the Meesho app. 2. Sarch for the Shirt. 3. Select the Shirt. 4. Select the Size. 5.Click on Buy Now button. 6. Select the address. 7. Click on Deliver To This Address. 8. Select the Payment method. 9. Click on COD. 10. Click on Contunue. 11. Click on Place Order. | 1. Search : Shirt 2. Payment : COD. | user is not able to Buy a Shirt with out Selecting Size. | user is not able to Buy a Shirt with out Selecting Size. | Pass.
TC_Cash on Delivery_04 | TS_Cash on Delivery_01 | open the browser enter the url signup with user credentials | Verify user is not able to Buy a item if there is no item in Add to card. | 1. open the Meesho app. 2. Search for the item. 3. Click on Add Cart. 4. Click on Continue. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on COD. 9. Click on Contunue. 10. Click on Place Order. | 1. Search : item 2. Payment : COD. | user is not able to Buy a item if there is no item in Add to card. | user is not able to Buy a item if there is no item in Add to card. | Pass.
TC_Reselling the Order_01 | TS_Reselling the Order_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a item using Reselling the order. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on COD. 8. Click on Yes. 9. Enter the amount in your Margin text Field. 10. Click on Contunue. 11. Click on Place Order. | 1. Search : item 2. Payment : COD. 3. Your Margin: 444. | user is able to Buy a item using Reselling the order. | user is able to Buy a item using Reselling the order. | Pass.
TC_Reselling the Order_02 | TS_Reselling the Order_01 | open the browser enter the url signup with user credentials | Verify user able to view "No" and "Yes" radio Buttons in Reselling the oredr. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on COD. 8. Click on Yes. | 1. Search : item 2. Payment : COD. | user able to view "No" and "Yes" radio Buttons in Reselling the oredr. | user able to view "No" and "Yes" radio Buttons in Reselling the oredr. | Pass.
TC_Reselling the Order_03 | TS_Reselling the Order_01 | open the browser enter the url signup with user credentials | Verify user able to Select the "No" and "Yes" radio Buttons in Reselling the oredr. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on COD. 9. Click on Yes. | 1. Search : item 2. Payment : COD. | user able to Select the "No" and "Yes" radio Buttons in Reselling the oredr. | user able to Select the "No" and "Yes" radio Buttons in Reselling the oredr. | Pass.
TC_Reselling the Order_04 | TS_Reselling the Order_01 | open the browser enter the url signup with user credentials | Verify user able to enter the Amount in your margin Text filed | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on COD. 8. Click on Yes. 9. Enter the amount in your Margin text Field. 10. Click on Contunue. 11. Click on Place Order. | 1. Search : item 2. Payment : COD. 3. Your Margin: 424. | user able to enter the Amount in your margin Text filed | user able to enter the Amount in your margin Text filed | Pass.
TC_Reselling the Order_05 | TS_Reselling the Order_01 | open the browser enter the url signup with user credentials | Verify user should not able to enter more then 8 numbers as a amount in Your Margin. | 1. open the Meesho app. 2. Search for the item. 3. Click on Buy Now. 4. Select the address. 5. Click on Delivery To This Address. 6. Select the Payment method. 7. Click on COD. 8. Click on Yes. 9. Enter the amount in your Margin text Field. 10. Click on Contunue. 12. Click on Place Order. | 1. Search : item 2. Payment : COD. 3. Your Margin: 1234567897. | user should not able to enter more then 8 numbers as a amount in Your Margin. | user should not able to enter more then 8 numbers as a amount in Your Margin. | Pass.
TC_Buy Now_01 | TS_Buy Now_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy product. | 1. open the Meesho app. 2. Select the product. 3.Click on Buy Now button. 4. Select the address. 5. Click on Deliver To This Address. 6. Select the Payment method. 7. Click on COD. 8. Click on Contunue. 9. Click on Place Order. | 1. Search : Product 2. Payment : COD. | user is able to Buy product. | user is able to Buy product. | Pass.
TC_Buy Now_02 | TS_Buy Now_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a Shirt by Selecting Size. | 1. open the Meesho app. 2. Sarch for the Shirt. 3. Select the Shirt. 4. Select the Size. 5.Click on Buy Now button. 6. Select the address. 7. Click on Deliver To This Address. 8. Select the Payment method. 9. Click on COD. 10. Click on Contunue. 11. Click on Place Order. | 1. Search : Shirt 2. Payment : COD. | user is able to Buy a Shirt by Selecting Size. | user is able to Buy a Shirt by Selecting Size. | Pass.
TC_Buy Now_03 | TS_Buy Now_01 | open the browser enter the url signup with user credentials | Verify user is able to Buy a item by Add to Cart. | 1. open the Meesho app. 2. Search for the item. 3. Click on Add Cart. 4. Click on Continue. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Click on COD. 9. Click on Contunue. 10. Click on Place Order. | 1. Search : item 2. Payment : COD. | user is able to Buy a item by Add to Cart. | user is able to Buy a item by Add to Cart. | Pass.
TC_Buy Now_04 | TS_Buy Now_01 | open the browser enter the url signup with user credentials | Verify user able to buy a product by clicking on Pay Now Button. | 1. open the Meesho app. 2. Search for the Product. 3. Click on Buy Now. 5. Select the address. 6. Click on Delivery To This Address. 7. Select the Payment method. 8. Select UPI Option. 9. Click on Enter UPI ID. 10. Enter the UPI ID in UPI ID text Field. 11.Click on verify Button. 12. Click on Contunue. 13. Click on Place Order. 14. Click on Pay Now. | 1. Search : item 2. Payment : UPI. | user able to buy a product by clicking on Pay Now Button. | user able to buy a product by clicking on Pay Now Button. | Pass.

## Defect report
DEFECT REPORT
Defect ID | Module Name | Defect Summary | Defect Priority | Assigned To | Status
DF_Wallet_01 | Wallet | uesr should not able to view Amazon Pay Wallet option | Low | chinna@gmail.com | To DO

## RTM
REQUIREMENTS TRACEABILITY MATRIX
BR_ID | TR_ID | TS_ID | Test Case ID | Status | DR_ID
BR_Payment page | TR_UPI_01 | TS_UPI_01 | TC_UPI_01 | Passed
|  |  | TC_UPI_02 | Passed
|  |  | TC_UPI_03 | Passed
|  |  | TC_UPI_04 | Passed
|  |  | TC_UPI_05 | Passed
| TR_Wallet_01 | TS_Wallet_01 | TC_Wallet_01 | Passed
|  |  | TC_Wallet_02 | Passed
|  |  | TC_Wallet_03 | Passed
|  |  | TC_Wallet_04 | Passed
|  |  | TC_Wallet_05 | Passed
|  |  | TC_Wallet_06 | Failed | DF_Wallet_01
| TR_Debit/Credit Card_01 | TS_Debit/Credit Card_01 | TC_Debit/Credit Card_01 | Passed
|  |  | TC_Debit/Credit Card_02 | Passed
|  |  | TC_Debit/Credit Card_03 | Passed
|  |  | TC_Debit/Credit Card_04 | Passed
|  |  | TC_Debit/Credit Card_05 | Passed
|  |  | TC_Debit/Credit Card_06 | Passed
|  |  | TC_Debit/Credit Card_07 | Passed
|  |  | TC_Debit/Credit Card_08 | Passed
|  |  | TC_Debit/Credit Card_09 | Passed
|  |  | TC_Debit/Credit Card_10 | Passed
|  |  | TC_Debit/Credit Card_11 | Passed
|  |  | TC_Debit/Credit Card_12 | Passed
|  |  | TC_Debit/Credit Card_13 | Passed
|  |  | TC_Debit/Credit Card_14 | Passed
| TR_Net Banking_01 | TS_Net Banking_01 | TC_Net Banking_01 | Passed
|  |  | TC_Net Banking_02 | Passed
|  |  | TC_Net Banking_03 | Passed
|  |  | TC_Net Banking_04 | Passed
|  |  | TC_Net Banking_05 | Passed
|  |  | TC_Net Banking_06 | Passed
|  |  | TC_Net Banking_07 | Passed
| TR_Cash on Delivery_01 | TS_Cash on Delivery_01 | TC_Cash on Delivery_01 | Passed
|  |  | TC_Cash on Delivery_02 | Passed
|  |  | TC_Cash on Delivery_03 | Passed
|  |  | TC_Cash on Delivery_04 | Passed
| TR_Reselling the Order_01 | TS_Reselling the Order_01 | TC_Reselling the Order_01 | Passed
|  |  | TC_Reselling the Order_02 | Passed
|  |  | TC_Reselling the Order_03 | Passed
|  |  | TC_Reselling the Order_04 | Passed
|  |  | TC_Reselling the Order_05 | Passed
| TR_Buy Now_01 | TS_Buy Now_01 | TC_Buy Now_01 | Passed
|  |  | TC_Buy Now_02 | Passed
|  |  | TC_Buy Now_03 | Passed
|  |  | TC_Buy Now_04 | Passed

## Summary
TEST EXECUTION SUMMARY
Project Name | Module Name | Total Cases | Total Passed | Total Failed | Total Executed | Pass Percentage | Fail Percentage | Complition Percentage
Meesho | Payment | 45 | 44 | 1 | 45 | 99% | 1% | 100%